## Grantt_Chart
PROJECT TITLE | VEHICLE TELEMATICS SYSTEMS, THE KEY TO SMART CARS
DATE | 15-10-2022
ID | TITLE | Assigned to | START DATE | DESCRIPTION | ESTIMATED HOURS | COMPLETE | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
1 | Searching for hardware components | Youssef Habib, Ahmed Samir, Mina Nadi, Moustafa Wahdan, Mohamed Nabil | 16-10-2022
1.1 | Looking for a DSRC Module that uses a commonly known interface(UART, SPI, I2C,...). | * Abbas - Moustafa Wahdan - Mina | 18-10-2022 | getting this module shipped is pretty difficult |  | UNDER TESTING | WEEK 9: Testing ESP32s; WEEK 10: Testing ESP32s
1.2 | Looking for a GNSS module, if possible GNSS with a cellular modem for (internet connectivity + localization) in one unit. also with commonly known interface. | * Ahmed Samir -Mina Nadi | 18-10-2022 | Ublox NEO-6mV2 GPS Module https://www.amazon.eg/-/en/Generic-Ublox-NEO-6mV2-GPS-Module/dp/B0BBNFF9SR/ref=asc_df_B0BBNFF9SR/?tag=egoshpadde-21&linkCode=df0&hvadid=545278985510&hvpos=&hvnetw=g&hvrand=1119724008382909294&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9112369&hvtargid=pla-1807030199197&psc=1 https://lastminuteengineers.com/neo6m-gps-arduino-tutorial/ |  | YES | WEEK 10: Brought up UBLOX NEO-7
1.3 | Looking for a 4G Modem with commonly known interface. | * Emad - Ali - Abbas | 18-10-2022 | [1] - BG96 LTE Dongle 4G Modem with UART Interface [2]- |  | YES | WEEK 10: Brought up a a 4G modem to ethernet
1.5 | Looking for a microcomputer to be used as our application processor, it will be doing the missions of the TCU. | * Abbas - Moustafa Wahdan - Ahmed Samir - Nada Ibrahim | 18-10-2022 | Rasppery PI 4-B |  | YES | WEEK 6: Brought up raspberry pi 4B
1.6 | Looking for an electrical vehicle to be used for the project demonstration. size around 120 * 60 cm2. | * Ahmed Tarek - Toqa Hossni - Moahmed Nabil | 18-10-2022 |  |  | WORK IN PROGRESS
1.7 | SPI to Ethernet module | * Mina - Abbas | 30-11-2022 | SPI to Ethernet Hardware TCP/IP W5500 https://free-electronic.com/product/spi-to-ethernet-hardware-tcp-ip-w5500-ethernet-network-module/ |  | YES | WEEK 10: Brought up SPI to Ethernet Hardware TCP/IP W5500
2 | Searching for the best cloud server provider & prices
2.1 | research on Digital ocean pricing | - Moustafa Wahdan | 19-10-2022 | Digital ocean starts from 4$/month and gives 200$ free credits for 1st 2 months and does not provide GPU https://www.digitalocean.com/pricing?utm_campaign=emea_brand_kw_en_cpc&utm_adgroup=digitalocean_pricing_exact&_keyword=digitalocean%20pricing&_device=c&_adposition=&utm_content=conversion&utm_medium=cpc&utm_source=google&gclid=Cj0KCQjw48OaBhDWARIsAMd966BoA9Mx-NZ536gDCjNrLRX51ICwgD-KZw_SszYGHk5HzKm6fhsUClUaAoTPEALw_wcB |  | WORK IN PROGRESS
2.2 | research on Linode pricing | - Moustafa Wahdan | 19-10-2022 | Less expensive than Digital ocean but gives only 100$ free credits but has some problems with ports https://www.linode.com/pricing/ |  | WORK IN PROGRESS
2.3 | research on Amazon aws pricing | - Moustafa Wahdan | 19-10-2022 | Gives 1 year free server but with weak capabilities https://aws.amazon.com/pricing/?aws-products-pricing.sort-by=item.additionalFields.productNameLowercase&aws-products-pricing.sort-order=asc&awsf.Free%20Tier%20Type=*all&awsf.tech-category=*all |  | WORK IN PROGRESS
2.1 | Resources
2.1.1 | Research for the best domain name in terms of the name and the price | - Nada Ibrahim | 20-10-2022 |  |  | WORK IN PROGRESS
2.1.2 | Check e-sync aliance https://esyncalliance.org/ | - Whole team |  |  |  | WORK IN PROGRESS
2.1.3 | Check ISO standards https://forallsecure.com/blog/unece-unr155-unr156 | - Whole team |  |  |  | WORK IN PROGRESS
2.1.4 | broadr-reach ethernet https://www.electronicdesign.com/markets/automotive/article/21806576/whats-the-difference-between-broadrreach-and-100baset1 |  |  |  |  | WORK IN PROGRESS
2.1.5 | Light weight ip stack | - Whole team |  |  |  | WORK IN PROGRESS
2.1.6 | AVNU https://avnu.org/ |  |  |  |  | WORK IN PROGRESS
2.1.7 | Auto CDS 1.4 / 1.6 IEEE 802.1as | - Whole team |  |  |  | WORK IN PROGRESS
2.1.8 | PTP https://www.youtube.com/watch?v=kJcmPg-qIFA |  |  |  |  | WORK IN PROGRESS
3 | Hardware Design
3.1 | Draw system diagram <HW> | - Whole team | 2022-01-12 |  |  | WORK IN PROGRESS
4 | Mobile App |  |  |  |  | NOT STARTED
4.1 | UI design for mobile app | * Toqa | 30-11-2022 |  |  | WORK IN PROGRESS
4.2 | Implement Log in page | *Nada - Wahdan -Toqa
5 | Network Access Device (NAD)
5.1 | Implemenet SOME/IP service and client that reads data from GPS module. | * Abbas - Mina | 30-11-2022 |  |  | NOT STARTED
5.2 | Implement service that accumulate data from multiple SOME/IP services and send it to back end server. | * Abbas - Wahdan - Samir | 30-11-2022 |  |  | NOT STARTED
5.3 | Implement SOME/IP service that receives data from speed sensor through ethernet. | - TBD |  |  |  | NOT STARTED
6 | Bare metal work
6.1 | Implement library to ease data sending using SPI to ethernet module | * Mina - Nabil - Emad - Ali | 30-11-2022 | Test using a simple python script listens at certain port number |  | YES
7 | DSRC module implementation for (V2V)
7.1 | Using two nodes of ESP32 test data exchange using ESPnow protocol | * Samir - Mina | 30-11-2022 | Test data exchange and connection process |  | YES
7.2 | [5 empty] | NOT STARTED
7.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED
4.3 | [5 empty] | NOT STARTED