## Grantt_Chart
October
TITLE | Comment | COMPLETE
Searching for hardware components |  | YES | WEB/MOBILE
Look for a DSRC Module that uses a commonly known interface(UART, SPI, I2C,...). | getting this module shipped is difficult | YES | EMBEDDED
Look for a GNSS module | Ublox NEO-7M | YES | BOTH
Look for a 4G Modem with commonly known interface. | Brought up a a 4G modem to ethernet | YES
Look for a microcomputer to be used as our application processor, it will be doing the missions of the TCU. | Rasppery PI 4-B | YES
Look for an electrical vehicle to be used for the project demonstration. size around 120 * 60 cm2. |  | WORK IN PROGRESS
Searching for the best cloud server provider & prices |  | YES
research on Digital ocean pricing | Digital ocean starts from 4$/month and gives 200$ free credits for 1st 2 months and does not provide GPU | YES
research on Linode pricing | Less expensive than Digital ocean but gives only 100$ free credits but has some problems with ports | YES
research on Amazon aws pricing | Gives 1 year free server but with weak capabilities | YES
Research for the best domain name in terms of the name and the price |  | YES
Review standards, protocols and research papers |  | YES
Review e-sync aliance | https://esyncalliance.org/ | YES
Review ISO standards | https://forallsecure.com/blog/unece-unr155-unr156 | YES
Time synchronization | PTP | WORK IN PROGRESS
November
TITLE | Comment | COMPLETE
Design hardware architecture |  | YES
Implement library to ease data sending using SPI to ethernet module | Test using a simple python script listens at certain port number | YES
Using two nodes of ESP32 test data exchange using ESP-NOW protocol | Test data exchange and connection process | YES
Decide on softwares used for Web/Mobile development |  | YES
Design system architecture for Web/Mobile |  | YES
December
TITLE | Comment | COMPLETE
Draw system diagram for whole project |  | YES
Design database Schema&ER diagram |  | YES
Run the SQL statements in a PostGreSQl database and wrap it all up as a micro service |  | YES
Project github organization | https://github.com/Vehicle-Telematics-Control-Unit | YES
SPI to Ethernet module | SPI2Ethernet W5500 | YES
January
TITLE | Comment | COMPLETE
Mobile App |  | WORK IN PROGRESS
UI design for mobile app |  | WORK IN PROGRESS
Implement Log-in page |  | YES
Implement Verification Page |  | YES
Create Splash screen |  | YES
Design and code an efficient encoder&decoder for making payloads | https://github.com/Vehicle-Telematics-Control-Unit/Efficent-encoder-decoder | YES
Create the relations in the ERD-diagram |  | YES
Review localization research papers |  | YES
February
TITLE | Comment | COMPLETE
Read GPS data on Linux (USB) |  | YES
Read GPS data using Raspberry-pi (SPI) |  | WORK IN PROGRESS
Exchange payloads from TCU to other TCU using ESP-NOW |  | WORK IN PROGRESS
VSOME/IP implementation and test |  | YES
Get Compass data from MPU 6050 on TCU |  | WORK IN PROGRESS
Create interface to connect the vehicle owner to his primary device on purchase |  | WORK IN PROGRESS
Create an api for user login from mobile app. |  | WORK IN PROGRESS
Create an api for the user submit a request to stop car and get a live location of vehicle. |  | NOT STARTED
Create Home page for Mobile App |  | WORK IN PROGRESS
Create Interface to Register that a new software update has been released |  | WORK IN PROGRESS
follows esync alliance statndards |  | WORK IN PROGRESS
Future
TITLE | Comment | COMPLETE
Create CI/CD pipelines using github actions + jenkins |  | NOT STARTED
Create a micro-service that contains a jenkins server |  | NOT STARTED
Implemenet SOME/IP service and client that reads data from GPS module. |  | NOT STARTED
Implement service that accumulate data from multiple SOME/IP services and send it to back end server. |  | NOT STARTED
Implement SOME/IP service that receives data from speed sensor through ethernet. |  | NOT STARTED
Services Containerization (Embedded) |  | NOT STARTED
Create web api for the vehicle to submit it's information and generate a diagnostics report based on it's information. including the recommended actions like maintenance. |  | NOT STARTED
Create web api for vehicle to send an alert of any malfunction as soon as it happens |  | NOT STARTED
Services Containerization (WEB) |  | NOT STARTED
Create a custom linux image (Yocto) |  | NOT STARTED
Localization Improvement KALMAN Filter |  | NOT STARTED
Localization Improvement ML approach |  | NOT STARTED
Integration of all sensors with SPI2Ethernet |  | NOT STARTED
Implement services and drivers for all sensors connected directly on TCU |  | WORK IN PROGRESS
Integrate TCU, DSRC(alternative) with all sensors |  | NOT STARTED
Integrate Embedded module With Web module through APIs |  | NOT STARTED
Create a thumbnail for notifications for mobile App (UI/UX) |  | NOT STARTED
Create a page with live gps location on google map |  | NOT STARTED
Create page that has a scannable qrcode to scan the vehicle access share request |  | NOT STARTED
Create page with a qr scanner to scan the qrcode and send the request to the server |  | NOT STARTED